## Sheet1
Date | Test Conditions | Issue faced | Issue status | Solution
2024-09-13 | Load cell testing | Test bed side displayed invalid input on serial monitor | Solved | Default case was getting executed every cycle when input wasn't received
2024-09-14
2024-09-15 | Complete test | Weight indicator malfunction due to white wire (SENSE-) coming off on Load cell connector end. | Solved | White wire (SENSE-) was resoldered properly
2024-09-16 | Complete test. Testbed side was located inside the workshop. Ground side was located near the gate of the Student Activity Centre. | No issues | NA | NA
2024-09-17 | Range testing along with ignition. No load cell included. Testbed side was located near chemical block. Ground side was located in the Recreation centre's vicinity | Communication inconsistent after 700m. | Unsolved | Requires revisitation later
|  | Inadvertent transition to launch state after arming. Concurrent with loosening/coming off of jumper connected to pin 3 of arduino and pull down resistor. | Solved
2024-09-18 | NA | No test done | NA | NA
2024-09-19 | Complete test | No issues | NA | NA
2024-09-20 | Midsem break
2024-09-21
2024-09-22
2024-09-23 | Midsemester Examinations
2024-09-24
2024-09-25
2024-09-26
2024-09-27
2024-09-28
2024-09-29 | Regular testing of load cell and weight indicator | There were fluctuations in weight indicator readings
2024-09-30 | Range test for RYLR + load cell data logging as motor test prep | Fluctuations in weight indicator readings, and loose jumper cables | In Progress | Switched the groundside microcontroller to Arduino MKRZero instead of Arduino Uno so that female jumpers on male pins will be more secure, saving that point of failure. Also taped wires, and will tape down the circuit to keep it secure
2024-10-01 | Data Transmission Test at small LOS range in ws | Data printing/ logging/ transmission rate is very slow (500ms per reading). Even on checking w/o any functions, simple ODR seems very low | Solved | Changed to analog from serial, thus getting around 22 readings per second.
2024-10-02 | Calibration of weight indicator | The load cell was not well caibrated enough, the readings are off by more than 10 N | In Progress | Changed code to calibrate before setup, but that isnt working well